## Sheet1
Steps | Task | Comments
1 | Prepare NDD and submit it for TPR review and review held from by Monday
2 | Submit the NDD after TPR approval in NSDP portal. | Change can be raise in prior to NSDR approval
3 | raise request for DNS and add device in Netinfo
4 | Lock Down the chanage by Friday | If we are planning for the change to go on next weekends
5 | Add change in NPMS and get it approved by Friday
6 | Send the cabling sheet to DCSD and ask for console and temporary access
7 | Get the change approved in the calls NAM-Tuesday Call only, 9:30PM APAC- James's call Monday @1:00PM, Wednesday@7:30AM & 12:30PM
8 | Get it approved all the change task as well as for group task
9 | Once change is approved. Send the pre notification
10 | Get it implemented as per the change and take pre and post checks
11 | Once change is completed, send the post notification, check DNS entry
12 | Close the change and update the NPMS
13 | Close the project in NPMS